## Sheet1
Working Draft | Corresponded Issue ID | Discussion | Contents | Merged to Draft | Line by Line Review and refine | Spec. Freeze (GGFeditor review/Public review)
TOC |  | done (May F2F) | - | done (May F2F) | Sep - Oct | Oct | done
1. Introduction |  | - | cited from Strawman | 7/20 telconf | Sep - Oct | Oct | working
2. Requirement | 1530, 1522 | done (May F2F) | done (May F2F) | 7/20 telconf | Sep - Oct | Oct | next telconf
3. Architecture | - | - | - | - | - | Oct | not yet
Concept and Terminology (detailed explanation of glossary) |  | Continueing | Aug F2F | Aug | Sep - Oct | Oct
Version Management | 1522 | Aug F2F | Aug | Aug | Sep - Oct | Oct
Data Transport (related to Register/Create, Update, GetContets operation) | 1543 | Done except for below TBDs: - Server location for Register - SOAP attachment detail | Aug F2F | Aug | Sep - Oct | Oct
Asynchronous Messaging | 1544 | Aug F2F | Aug | Aug | Sep - Oct | Oct
Collaboration with Other OGSA Services | 1535 | Done for CDDLM in the joint session at GGF14. | Aug | Aug | Sep - Oct | Oct
4. Example Usage | - | - | - | - | - | Oct
Role definition |  | done (7/13 telconf) | Aug | Aug | Sep - Oct | Oct
AA Creation |  | 7/20 telconf | Aug | Aug | Sep - Oct | Oct
AA Modifcation |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
AA Deletion |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
AA Replication |  | working | Aug - Sep | Sep | Sep - Oct | Oct
5. ARI spec | 1525, 1537, 1538, 1539 | working after Architecture ? | Aug - Sep | Sep | Sep - Oct | Oct
6. AAF spec (related to SDD spec) |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
7. Security Consideration |  | working | Aug - Sep | Sep | Sep - Oct | Oct
8. Samples |  | - | after the complete schema is defined |  | Sep - Oct | Oct
9. Schema Definition |  | - | along with ARI/AAF contents |  | Sep - Oct | Oct
Glossary |  | done (GGF14) | done (7/13 telconf) | done (7/13 telconf) | Sep - Oct | Oct