{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["20050810","20050726","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"20050810","index":0,"n_rows":22,"n_cols":8,"rows_kept":22,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Working Draft","Corresponded\nIssue ID","Discussion","Contents","Merged to Draft","Line by Line Review\nand refine","Spec. Freeze\n(GGFeditor review/Public review)"]
["TOC",null,"done (May F2F)","-","done (May F2F)","Mid Sep","Oct"]
["1. Introduction",null,"-","cited from Strawman","7/20 telconf","Mid Sep","Oct","Color Code:"]
["2. Requirement","1530, 1522","done (May F2F)","done (May F2F)","7/20 telconf","Mid Sep","Oct","done"]
["3. Architecture","-","-","-","-","-","Oct","working"]
["    Concept and Terminology\n    (detailed explanation of glossary)",null,"Aug F2F","by End of Aug","after 1 week review","Mid Sep","Oct","next telconf"]
["    Version Management",1522,"August ML","by End of Aug","after 1 week review","Mid Sep","Oct","not yet"]
["    Data Transport\n    (related to Register/Create, \n     Update, GetContets operation)",1543,"Aug F2F","by End of Aug","after 1 week review","Mid Sep","Oct"]
["    Asynchronous Messaging",1544,"Aug F2F","by End of Aug","after 1 week review","Mid Sep","Oct"]
["    Collaboration with Other OGSA \n     Services",1535,"Done for CDDLM in the joint session at GGF14.","by End of Aug","after 1 week review","Mid Sep","Oct"]
["4. Example Usage","-","-","-","-","-","Oct"]
["    Role definition",null,"7/13 telconf","by Mid of Sep","after 1 week review","Late Sep","Oct"]
["    AA Creation",null,"Aug F2F","by Mid of Sep","after 1 week review","Late Sep","Oct"]
["    AA Modifcation",null,"Aug F2F","by Mid of Sep","after 1 week review","Late Sep","Oct"]
["    AA Deletion",null,"Aug F2F","by Mid of Sep","after 1 week review","Late Sep","Oct"]
["    AA Replication",null,"working ","by Mid of Sep","after 1 week review","Late Sep","Oct"]
["5. ARI spec","1525, 1537, \n1538, 1539","Aug F2F","by end of Sep","after 1 week review","Late Sep","Oct"]
["6. AAF spec   (related to SDD spec)",null,"Aug F2F","by end of Sep","after 1 week review","Late Sep","Oct"]
["7. Security Consideration",null,"working ","by End of Aug","after 1 week review","Late Sep","Oct"]
["8. Samples",null,"-","by end of Sep","after 1 week review","Late Sep","Oct"]
["9. Schema Definition",null,"- ","by end of Sep","after 1 week review","Late Sep","Oct"]
["Glossary",null,"done (GGF14)","done (7/13 telconf)","done (7/13 telconf)","Late Sep","Oct"]

{"sheet":"20050726","index":1,"n_rows":22,"n_cols":8,"rows_kept":22,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["Working Draft","Corresponded\nIssue ID","Discussion","Contents","Merged to Draft","Line by Line Review\nand refine","Spec. Freeze\n(GGFeditor review/Public review)"]
["TOC",null,"done (May F2F)","-","done (May F2F)","Sep - Oct","Oct","done"]
["1. Introduction",null,"-","cited from Strawman","7/20 telconf","Sep - Oct","Oct","working"]
["2. Requirement","1530, 1522","done (May F2F)","done (May F2F)","7/20 telconf","Sep - Oct","Oct","next telconf"]
["3. Architecture","-","-","-","-","-","Oct","not yet"]
["    Concept and Terminology\n    (detailed explanation of glossary)",null,"Continueing ","Aug F2F","Aug","Sep - Oct","Oct"]
["    Version Management",1522,"Aug F2F","Aug ","Aug","Sep - Oct","Oct"]
["    Data Transport\n    (related to Register/Create, \n     Update, GetContets operation)",1543,"Done except for below TBDs:\n- Server location for Register\n- SOAP attachment detail","Aug F2F","Aug","Sep - Oct","Oct"]
["    Asynchronous Messaging",1544,"Aug F2F","Aug ","Aug","Sep - Oct","Oct"]
["    Collaboration with Other OGSA \n     Services",1535,"Done for CDDLM in the joint session at GGF14.","Aug ","Aug","Sep - Oct","Oct"]
["4. Example Usage","-","-","-","-","-","Oct"]
["    Role definition",null,"done (7/13 telconf)","Aug ","Aug","Sep - Oct","Oct"]
["    AA Creation",null,"7/20 telconf","Aug ","Aug","Sep - Oct","Oct"]
["    AA Modifcation",null,"Aug F2F","Aug - Sep","Sep","Sep - Oct","Oct"]
["    AA Deletion",null,"Aug F2F","Aug - Sep","Sep","Sep - Oct","Oct"]
["    AA Replication",null,"working ","Aug - Sep","Sep","Sep - Oct","Oct"]
["5. ARI spec","1525, 1537, \n1538, 1539","working \nafter Architecture ?","Aug - Sep","Sep","Sep - Oct","Oct"]
["6. AAF spec   (related to SDD spec)",null,"Aug F2F","Aug - Sep","Sep","Sep - Oct","Oct"]
["7. Security Consideration",null,"working ","Aug - Sep","Sep","Sep - Oct","Oct"]
["8. Samples",null,"-","after the complete schema is defined",null,"Sep - Oct","Oct"]
["9. Schema Definition",null,"- ","along with ARI/AAF contents",null,"Sep - Oct","Oct"]
["Glossary",null,"done (GGF14)","done (7/13 telconf)","done (7/13 telconf)","Sep - Oct","Oct"]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}