## 20050919
Color Code: | done | working | next telconf | not yet
Working Draft Proposed Spec. Freeze (Submit to GGF editor): 10/13 | Issue ID | Discussion | Contents | Editor | Merged to Draft | Line by Line Review
TOC |  | May F2F | - |  | May F2F | Mid Sep
1. Introduction |  | done | Strawman |  | 7/20 telconf | Mid Sep
2. Requirement | 1530, 1522 | May F2F | May F2F |  | 7/20 telconf | Mid Sep
3. Architecture | - | - | - |  | - | -
3.1 Concepts | - | - | - |  | - | -
3.1.1 Application Archive and Repository |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.2 AA Structure |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.3 Physical Format of the AA |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.4 Relationship between AA and Job |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.5 AA Identifier and Endpoint Reference |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.6 Version Control | 1522 | on ML | 9/20 | KF | 9/19 | Mid Sep
3.2 Design Policy | - | - | - |  | - | -
3.2.1 OGSA WSRF Basic Profile compliant |  | Aug F2F | 9/7 | Sachiko | 9/19 | Mid Sep
3.2.2 Data Handling | 1543 | Aug F2F | 9/7 | Sachiko | 9/19 | Mid Sep
3.2.3 Asynchronous Messaging | 1544 | Aug F2F | 9/7 | Sachiko | 9/19 | Mid Sep
3.2 Relationship to other activities | - | - | - |  | - | -
3.3.1 OGSA SDD TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
3.3.2 OGSA EMS Design Team |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.3 OGSA CDDLM WG | 1535 | Aug F2F | 9/14 | KF | 9/19 | Mid Sep
3.3.4 OGSA Data WG |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.5 OASIS WSDM TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
4. Example Usage | - | - | - |  | - | -
4.1 Role definition |  | 7/13 telconf | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.2 AA Creation |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.3 AA Read |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.4 AA Update |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.5 AA Delete |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.6 AA Replicate |  | working | ? | Pete | after 1 week review | Late Sep
5. ARI spec | 1525, 1537, 1538, 1539 | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
6. Manageability |  | May F2F | 9/19 | Tom
7. AAF spec (related to SDD spec) |  | Aug F2F | 9/28 | ? | after 1 week review | Late Sep
8. Security Consideration |  | 8/10 teleconf | 9/19 | Mike | 9/19 | Late Sep
9. Samples |  | - | GGF15 | ? | after 1 week review | Late Sep
10. Schema Definition |  | - | GGF15 | ? | ? | ?
11. Open Issue (Toward V2?) |  | - | GGF15 | ? | ? | ?
Glossary |  | GGF14 | 7/13 telconf |  | 7/13 telconf | Late Sep

## 20050915
Color Code: | done | working | next telconf | not yet
Working Draft Proposed Spec. Freeze (Submit to GGF editor): 10/13 | Issue ID | Discussion | Contents | Editor | Merged to Draft | Line by Line Review
TOC |  | May F2F | - |  | May F2F | Mid Sep
1. Introduction |  | done | Strawman |  | 7/20 telconf | Mid Sep
2. Requirement | 1530, 1522 | May F2F | May F2F |  | 7/20 telconf | Mid Sep
3. Architecture | - | - | - |  | - | -
3.1 Concepts | - | - | - |  | - | -
3.1.1 Application Archive and Repository |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.2 AA Structure |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.3 Physical Format of the AA |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.4 Relationship between AA and Job |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.5 AA Identifier and Endpoint Reference |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.6 Version Control | 1522 | on ML | 9/28 | KF | after 1 week review | Mid Sep
3.2 Design Policy | - | - | - |  | - | -
3.2.1 OGSA WSRF Basic Profile compliant |  | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.2 Data Handling | 1543 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.3 Asynchronous Messaging | 1544 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2 Relationship to other activities | - | - | - |  | - | -
3.3.1 OGSA SDD TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
3.3.2 OGSA EMS Design Team |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.3 OGSA CDDLM WG | 1535 | Aug F2F | 9/14 | KF | after 1 week review | Mid Sep
3.3.4 OGSA Data WG |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.5 OASIS WSDM TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
4. Example Usage | - | - | - |  | - | -
4.1 Role definition |  | 7/13 telconf | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.2 AA Creation |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.3 AA Read |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.4 AA Update |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.5 AA Delete |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.6 AA Replicate |  | working | ? | Pete | after 1 week review | Late Sep
5. ARI spec | 1525, 1537, 1538, 1539 | Aug F2F | 9/19 | KF, Sachiko | after 1 week review | Late Sep
6. Manageability |  | May F2F | 9/19 | Tom
7. AAF spec (related to SDD spec) |  | Aug F2F | 9/28 | ? | after 1 week review | Late Sep
8. Security Consideration |  | 8/10 teleconf | End of Aug | Mike | after 1 week review | Late Sep
9. Samples |  | - | 9/28 | ? | after 1 week review | Late Sep
10. Schema Definition |  | - | GGF15 | ? | ? | ?
11. Open Issue (Toward V2?) |  | - | GGF15 | ? | ? | ?
Glossary |  | GGF14 | 7/13 telconf |  | 7/13 telconf | Late Sep

## 20050914
Color Code: | done | working | next telconf | not yet
Working Draft Proposed Spec. Freeze (Submit to GGF editor): 10/13 | Issue ID | Discussion | Contents | Editor | Merged to Draft | Line by Line Review
TOC |  | May F2F | - |  | May F2F | Mid Sep
1. Introduction |  | done | Strawman |  | 7/20 telconf | Mid Sep
2. Requirement | 1530, 1522 | May F2F | May F2F |  | 7/20 telconf | Mid Sep
3. Architecture | - | - | - |  | - | -
3.1 Concepts | - | - | - |  | - | -
3.1.1 Application Archive and Repository |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.2 AA Structure |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.3 Physical Format of the AA |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.4 Relationship between AA and Job |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.5 AA Identifier and Endpoint Reference |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.6 Version Control | 1522 | on ML | End of Aug | ? | after 1 week review | Mid Sep
3.2 Design Policy | - | - | - |  | - | -
3.2.1 OGSA WSRF Basic Profile compliant |  | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.2 Data Handling | 1543 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.3 Asynchronous Messaging | 1544 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2 Relationship to other activities | - | - | - |  | - | -
3.3.1 OGSA SDD TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
3.3.2 OGSA EMS Design Team |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.3 OGSA CDDLM WG | 1535 | Aug F2F | 9/14 | KF | after 1 week review | Mid Sep
3.3.4 OGSA Data WG |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.5 OASIS WSDM TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
4. Example Usage | - | - | - |  | - | -
4.1 Role definition |  | 7/13 telconf | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.2 AA Creation |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.3 AA Read |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.4 AA Update |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.5 AA Delete |  | Aug F2F | 9/28 | KF, Sachiko | after 1 week review | Late Sep
4.6 AA Replicate |  | working | ? | Pete | after 1 week review | Late Sep
5. ARI spec | 1525, 1537, 1538, 1539 | Aug F2F | 9/19 | KF, Sachiko | after 1 week review | Late Sep
6. Manageability |  | May F2F | 9/19 | Tom
7. AAF spec (related to SDD spec) |  | Aug F2F | 9/28 | ? | after 1 week review | Late Sep
8. Security Consideration |  | 8/10 teleconf | End of Aug | Mike | after 1 week review | Late Sep
9. Samples |  | - | 9/28 | ? | after 1 week review | Late Sep
10. Schema Definition |  | - | GGF15 | ? | ? | ?
11. Open Issue (Toward V2?) |  | - | GGF15 | ? | ? | ?
Glossary |  | GGF14 | 7/13 telconf |  | 7/13 telconf | Late Sep

## 20050908
Color Code: | done | working | next telconf | not yet
Working Draft Proposed Spec. Freeze (Submit to GGF editor): 10/13 | Issue ID | Discussion | Contents | Editor | Merged to Draft | Line by Line Review
TOC |  | May F2F | - |  | May F2F | Mid Sep
1. Introduction |  | done | Strawman |  | 7/20 telconf | Mid Sep
2. Requirement | 1530, 1522 | May F2F | May F2F |  | 7/20 telconf | Mid Sep
3. Architecture | - | - | - |  | - | -
3.1 Concepts | - | - | - |  | - | -
3.1.1 Application Archive and Repository |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.2 AA Structure |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.3 Physical Format of the AA |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.4 Relationship between AA and Job |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.5 AA Identifier and Endpoint Reference |  | Aug F2F | 8/31 | Sachiko | 9/7 | Mid Sep
3.1.6 Version Control | 1522 | on ML | End of Aug | ? | after 1 week review | Mid Sep
3.2 Design Policy | - | - | - |  | - | -
3.2.1 OGSA WSRF Basic Profile compliant |  | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.2 Data Handling | 1543 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2.3 Asynchronous Messaging | 1544 | Aug F2F | 9/7 | Sachiko | after 1 week review | Mid Sep
3.2 Relationship to other activities | - | - | - |  | - | -
3.3.1 OGSA SDD TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
3.3.2 OGSA EMS Design Team |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.3 OGSA CDDLM WG | 1535 | Aug F2F | 9/14 | KF | after 1 week review | Mid Sep
3.3.4 OGSA Data WG |  | Aug F2F | 9/14 | Mike, Pete | after 1 week review | Mid Sep
3.3.5 OASIS WSDM TC |  | Aug F2F | 9/14 | Tom | after 1 week review | Mid Sep
4. Example Usage | - | - | - |  | - | -
4.1 Role definition |  | 7/13 telconf | 9/14 | KF, Sachiko | after 1 week review | Late Sep
4.2 AA Creation |  | Aug F2F | 9/14 | KF, Sachiko | after 1 week review | Late Sep
4.3 AA Read |  | Aug F2F | 9/14 | KF, Sachiko | after 1 week review | Late Sep
4.4 AA Update |  | Aug F2F | 9/14 | KF, Sachiko | after 1 week review | Late Sep
4.5 AA Delete |  | Aug F2F | 9/14 | KF, Sachiko | after 1 week review | Late Sep
4.6 AA Replicate |  | working | ? | Pete | after 1 week review | Late Sep
5. ARI spec | 1525, 1537, 1538, 1539 | Aug F2F | End of Sep | KF, Sachiko | after 1 week review | Late Sep
6. Manageability |  | May F2F | End of Sep | Tom
7. AAF spec (related to SDD spec) |  | Aug F2F | End of Sep | ? | after 1 week review | Late Sep
8. Security Consideration |  | 8/10 teleconf | End of Aug | Mike | after 1 week review | Late Sep
9. Samples |  | - | End of Sep | ? | after 1 week review | Late Sep
10. Schema Definition |  | - | GGF15 | ? | ? | ?
11. Open Issue (Toward V2?) |  | - | GGF15 | ? | ? | ?
Glossary |  | GGF14 | 7/13 telconf |  | 7/13 telconf | Late Sep

## 20050810
Working Draft | Corresponded Issue ID | Discussion | Contents | Merged to Draft | Line by Line Review and refine | Spec. Freeze (GGFeditor review/Public review)
TOC |  | done (May F2F) | - | done (May F2F) | Mid Sep | Oct
1. Introduction |  | - | cited from Strawman | 7/20 telconf | Mid Sep | Oct | Color Code:
2. Requirement | 1530, 1522 | done (May F2F) | done (May F2F) | 7/20 telconf | Mid Sep | Oct | done
3. Architecture | - | - | - | - | - | Oct | working
Concept and Terminology (detailed explanation of glossary) |  | Aug F2F | by End of Aug | after 1 week review | Mid Sep | Oct | next telconf
Version Management | 1522 | August ML | by End of Aug | after 1 week review | Mid Sep | Oct | not yet
Data Transport (related to Register/Create, Update, GetContets operation) | 1543 | Aug F2F | by End of Aug | after 1 week review | Mid Sep | Oct
Asynchronous Messaging | 1544 | Aug F2F | by End of Aug | after 1 week review | Mid Sep | Oct
Collaboration with Other OGSA Services | 1535 | Done for CDDLM in the joint session at GGF14. | by End of Aug | after 1 week review | Mid Sep | Oct
4. Example Usage | - | - | - | - | - | Oct
Role definition |  | 7/13 telconf | by Mid of Sep | after 1 week review | Late Sep | Oct
AA Creation |  | Aug F2F | by Mid of Sep | after 1 week review | Late Sep | Oct
AA Modifcation |  | Aug F2F | by Mid of Sep | after 1 week review | Late Sep | Oct
AA Deletion |  | Aug F2F | by Mid of Sep | after 1 week review | Late Sep | Oct
AA Replication |  | working | by Mid of Sep | after 1 week review | Late Sep | Oct
5. ARI spec | 1525, 1537, 1538, 1539 | Aug F2F | by end of Sep | after 1 week review | Late Sep | Oct
6. AAF spec (related to SDD spec) |  | Aug F2F | by end of Sep | after 1 week review | Late Sep | Oct
7. Security Consideration |  | working | by End of Aug | after 1 week review | Late Sep | Oct
8. Samples |  | - | by end of Sep | after 1 week review | Late Sep | Oct
9. Schema Definition |  | - | by end of Sep | after 1 week review | Late Sep | Oct
Glossary |  | done (GGF14) | done (7/13 telconf) | done (7/13 telconf) | Late Sep | Oct

## 20050726
Working Draft | Corresponded Issue ID | Discussion | Contents | Merged to Draft | Line by Line Review and refine | Spec. Freeze (GGFeditor review/Public review)
TOC |  | done (May F2F) | - | done (May F2F) | Sep - Oct | Oct | done
1. Introduction |  | - | cited from Strawman | 7/20 telconf | Sep - Oct | Oct | working
2. Requirement | 1530, 1522 | done (May F2F) | done (May F2F) | 7/20 telconf | Sep - Oct | Oct | next telconf
3. Architecture | - | - | - | - | - | Oct | not yet
Concept and Terminology (detailed explanation of glossary) |  | Continueing | Aug F2F | Aug | Sep - Oct | Oct
Version Management | 1522 | Aug F2F | Aug | Aug | Sep - Oct | Oct
Data Transport (related to Register/Create, Update, GetContets operation) | 1543 | Done except for below TBDs: - Server location for Register - SOAP attachment detail | Aug F2F | Aug | Sep - Oct | Oct
Asynchronous Messaging | 1544 | Aug F2F | Aug | Aug | Sep - Oct | Oct
Collaboration with Other OGSA Services | 1535 | Done for CDDLM in the joint session at GGF14. | Aug | Aug | Sep - Oct | Oct
4. Example Usage | - | - | - | - | - | Oct
Role definition |  | done (7/13 telconf) | Aug | Aug | Sep - Oct | Oct
AA Creation |  | 7/20 telconf | Aug | Aug | Sep - Oct | Oct
AA Modifcation |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
AA Deletion |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
AA Replication |  | working | Aug - Sep | Sep | Sep - Oct | Oct
5. ARI spec | 1525, 1537, 1538, 1539 | working after Architecture ? | Aug - Sep | Sep | Sep - Oct | Oct
6. AAF spec (related to SDD spec) |  | Aug F2F | Aug - Sep | Sep | Sep - Oct | Oct
7. Security Consideration |  | working | Aug - Sep | Sep | Sep - Oct | Oct
8. Samples |  | - | after the complete schema is defined |  | Sep - Oct | Oct
9. Schema Definition |  | - | along with ARI/AAF contents |  | Sep - Oct | Oct
Glossary |  | done (GGF14) | done (7/13 telconf) | done (7/13 telconf) | Sep - Oct | Oct