{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":13,"n_cols":6,"rows_kept":13,"flags":["formulas_cached_only"]}
["Area","Category/Project","Activity","Timeframe","Status","Notes"]
["All","GGF16","- Propose content",null,"CFP deadline Nov 30"]
["Community Affairs","GGF16","- IT Legal Issues BoF",null,"Julie to close with Mark Henley to setup BoF","Mark Henley offered to lead BoF"]
["Community Affairs","GGF16","- Propose session(s) for Israeli Association of Grid Technologies (IGT)",null,"Julie to encourage content submission to GGF16"]
["All ","Community Objectives","All ADs have approved"]
["All ","Area Objectives","- Each area director to define  mission, objectives and proposed projects/activities in support of overall","Final by Jan'06 F2F"]
["Major Grid Projects",null,"- Produce VOC and plan GGF16 meeting/sessions",null,"Victor to follow-up after SC05"]
["Community Affairs","IGT Community Group","- Create regional community group for The Israeli Association of Grid Technologies (IGT)",null,null,"Ref www.grid.org.il"]
["VC","Community Operations Model","- Implement BoA","By Jan'06 F2F"]
["VC","GGF Inter-Function Communicaton","- Develop cross-func objectives with Standards and Operations","By Jan'06 F2F"]
["Community Affairs","Community Survey","- Develop and execute periodic GGF Community Satisfaction Survey",null,"Outline developed, standards input solicited"]
["VC","Internal community communication mechanism","wiki",null,"Per IT Area, hardware/software upgrade in-process that will enable this"]
["VC/Community Affiars","External communication mechanism","web pages",null,"Outline developed, navigation proposal needed"]