## Discussion
Updated Date
Document Tracker |  | https://forge.gridforum.org/sf/docman/do/listDocuments/projects.graap-wg/docman.root.current_drafts
Comment Tracker |  | https://forge.gridforum.org/sf/discussion/do/listTopics/projects.ggf-editor/discussion.rec_ws_agreement_spec_0
Draft |  | http://www.ogf.org/Public_Comment_Docs/Documents/Oct-2006/WS-AgreementSpecificationDraftFinal_sp_tn_jpver_v2.pdf
Comment-ID | Link | Contents | Posted By | Status | Resolution/Discussion | Reflected in Draft? | Page/Section/line | Owner | Done?
1 | WS-Ag Comments | 1: In section 5.2, you should state that an agreement SHOULD agree (i.e. conform to) with any template on which it is based. This should not be a MUST though; the templates are not binding on the agreements | Donal Fellows
2 | WS-Ag Comments | 2: (Pure Editorial Issue) The diagram in section 7.1 is obviously sampled from elsewhere as it looks pixellated and ugly . Please redraw. (The diagrams in sections 7.2 and 7.3 are OK, except for a minor text clipping issue on the 'g' in " Processing" in the 7.2 diagram) | Donal Fellows | Done
3 | WS-Ag Comments | 3: (Pure Editorial Issue) There are asterisks (*) around some organization names in section 12, which looks bad. If those organizations are to be distinguished for some reason, use italics or bold. | Donal Fellows | Done but probably Volker's affiliation needs to be updated?
4 | WS-Ag Comments | 4: You really need to do a Primer, even more than JSDL needs one! | Donal Fellows
5 | WS-Ag Comments | 5: You do not clearly state that agreements refer to web-services. Please add a bit that does so (probably just a short clause), probably in both the abstract and in section 1.1. | Donal Fellows |  | Well it is referred in Section 3.. Copy essence of that into 1?
6 | WS-Ag Comments | 6: It would be nice if the Penalty (section 4.2.6.4.2) could describe multiple values in the same element ("$40 _and_ a free one-time license for Gaussian!") instead of having to describe several Penalty elements with the same AssessmentInterval. Might also want to allow both TimeInterval and Count to be present so that can state that for a particular penalty, it is assessed e.g. every 30 minutes but the penalty is only paid out once. | Donal Fellows
7 | WS-Ag Comments | 7: (Pure Editorial Issue) You're not consistent in your indenting. Don't you just love Word? I find that the only way I can solve this sort of thing is by minimizing the number of "styles in use"… | Donal Fellows |  | Leave it to a WORD wizard..(Not TN)
8 | WS-Ag Comments | 8: (Pure Editorial Issue) Only some URLs in the references are hyperlinks. Either all should be, or none should be. ("None" involves less work for you.) | Donal Fellows | Done (I think..)
9 | WS-Ag Comments | 9: (Pure Editorial Issue) Section names should be "Capitalized Properly", so Section 2.1's name needs to be "Job Submission" and 2.2's name needs to change to "Advance Reservation or Pre-Establishment of Resource Preferences" | Donal Fellows | Done
10 | WS-Ag Comments | 10: (Pure Editorial Issue) The document title probably shouldn't appear in the Contents, but this is surprisingly difficult to fix in Word without causing more chaos than is justifiable. | Donal Fellows | Done. (Thanks to Andreas Savva-san)
11 | WS-Ag Comments | 11: You should say more about Security Considerations since there are financial implications of an agreement. In particular, don't say "it may be desirable to authenticate the participants" but instead say "implementations SHOULD authenticate the participants". Then you need to say that the specification does not say how to do this, though you could point to the OGSA secure channel stuff as a way to do it. | Donal Fellows
12 | Improvements to WSDL'S and XSDs | (1) in AgreementState.wsdl <xs:complexType name="AgreementStatePropertiesType"> <xs:sequence> <xs:element ref="wsag:AgreementState" /> <xs:element ref="wsag:GuaranteeTermStateList" /> <xs:element ref="wsag:ServiceTermStateList" /> </xs:sequence> </xs:complexType> should be <xs:complexType name="AgreementStatePropertiesType"> <xs:sequence> <xs:element ref="wsag:AgreementState" /> <xs:element ref="wsag:GuaranteeTermState" minOccurs="0" maxOccurs="unbounded"/> <xs:element ref="wsag:ServiceTermState" minOccurs="0" maxOccurs="unbounded"/> </xs:sequence> </xs:complexType> It avoids the definition of additional type wsag:GuaranteeTermStateList and wsag:ServiceTermStateList. It is more consistent with the WSRF specification by giving individual access to each of the GuaranteeTermState and ServiceTermState items. Correspondingly, the current definition of wsag:GuaranteeTermStateList and wsag:ServiceTermStateList in agreement_state_types.xsd : <xsd:element name="GuaranteeTermStateList" type="wsag:GuaranteeTermStateListType" /> <xsd:element name="ServiceTermStateList" type="wsag:ServiceTermStateListType" /> should correspondingly be modified into <xsd:element name="GuaranteeTermState" type="wsag:GuaranteeTermStateType" /> <xsd:element name="ServiceTermState" type="wsag:ServiceTermStateType" /> | Tianchao Li |  | Tianchao has provided a modified wsdl/xsd. We need to get feedback from some of the implementors.
13 | Improvements to WSDL'S and XSDs | (2) Related with issue (1), I stongly suggest wsag:AgreementStateType and wsag:GuaranteeTermStateType and wsag: ServiceTermStateType defined in the way as the attached agreement_state_types.xsd . Take ServiceTermState for example. Briefly speaking, it defines the ServiceTermState as a global element to support issue(1). AND, the ServiceTermStateType extends the TermStateType and the corresponding type of state is defined as an attribute extension. ---original--- <xsd:complexType name="GuaranteeTermStateListType"> <xsd:choice maxOccurs="unbounded"> <xsd:element name="NotDetermined" type="wsag:TermStateType" /> <xsd:element name="Fulfilled" type="wsag:TermStateType" /> <xsd:element name="Violated" type="wsag:TermStateType" /> </xsd:choice> </xsd:complexType> ---suggestion--- <xs:complexType name="GuaranteeTermStateType"> <xs:complexContent> <xs:extension base="wsag:TermStateType"> <xs:attribute name="state"> <xs:simpleType> <xs:restriction base="xs:string"> <xs:enumeration value="NotDetermined" /> <xs:enumeration value="Fulfilled" /> <xs:enumeration value="Violated" /> </xs:restriction> </xs:simpleType> </xs:attribute> </xs:extension> </xs:complexContent> </xs:complexType> This also has several other practical advantages. First, if the state element has sub elements, the change of state will result into complicated XML process or Java object operations in the old definition and with the suggested definition you only need to change the state attribute of the corresponding element. Second, this definition is more consistent with the style of definition in agreement_types.xsd (look at the different term type definitions there). Last, both Globus and Axis 1.x has problem in stub generation for xsd:choice maxOccurs="unbounded". After all, this change does not result into the loss of constraint power and do not require modification of the current specification except for the XSD file itself. Please see the attached agreement_state_types.xsd file for modifications to AgreementStateType, TermStateType, in the same way. | Tianchao Li |  | Tianchao has provided a modified wsdl/xsd. We need to get feedback from some of the implementors.
14 | Improvements to WSDL'S and XSDs | (3) wsag:AgreementProperties has a sub element wsag:AgreementServiceReferenceList. It seems to be a duplication of the information in ServiceReference element of ServiceDescriptionTerm, which is another sub element of wsag:AgreementProperties. If I'm correct, then it should be removed. | Tianchao Li |  | Tianchao has provided a modified wsdl/xsd. We need to get feedback from some of the implementors.
15 | Naming Conventions Consistency | 1. Currently, all port types does not have input and output name, except for Agreement port type: <wsdl:input name="TerminateRequest" message="wsag:TerminateInputMessage" /> <wsdl:output name="TerminateResponse" message="wsag:TerminateOuputMessage"/> The name attribute should be removed for consistency. | Tianchao Li | Wait for feedback from WSDL guru's
16 | Naming Conventions Consistency | 2. the names for message names, message element names and message type names are not totally symmetric -- Agreement.wsdl TerminateInputMessage <-> TerminateOuputMessage TerminateInput <-> TerminateResponse (!) TerminateInputType <-> TerminateOutputType -- AgreementAcceptance.wsdl AcceptAgreementInputMessage <-> AcceptAgreementOuputMessage AcceptAgreementInput <-> AcceptAgreementResponse (!) AgreementAcceptanceInputType <-> AgreementAcceptanceOutputType RejectAgreementInputMessage <-> RejectAgreementOuputMessage RejectAgreementInput <-> RejectAgreementResponse (!) AgreementAcceptanceInputType <-> AgreementAcceptanceOutputType -- AgreementFactory.wsdl CreateAgreementInputMessage <-> CreateAgreementOuputMessage CreateAgreementInput <-> CreateAgreementResponse (!) CreateAgreementInputType <-> CreateAgreementOutputType -- PendingAgreementFactory.wsdl CreatePendingAgreementInputMessage <-> CreatePendingAgreementOuputMessage CreatePendingAgreementInput <-> CreatePendingAgreementResponse (!) CreatePendingAgreementInputType <-> CreatePendingAgreementOutputType Solution: TerminateResponse should be renamed TerminateOutput AcceptAgreementResponse should be renamed AcceptAgreementOutput RejectAgreementResponse should be renamed RejectAgreementOutput CreateAgreementResponse should be renamed CreateAgreementOutput CreatePendingAgreementResponse should be renamed CreatePendingAgreementOutput | Tianchao Li |  | Wait for feedback from WSDL guru's
17 | Comments on WS-Agreement | 1) In section 7.1 (Agreement States), the text "Terminated - The terminated state means that an Agreement offer has been terminated by the Agreement Initiator and that the obligation no longer exists. This state MAY follow Pending, PendingAndTerminating, Observed or ObservedAndTerminating when the termination decision is made." implies that a transition from Pending directly to Terminating is possible, yet no such transition is depicted in the diagram of the agreement state model. | Stephen Pickles |  | Probably yes
18 | Comments on WS-Agreement | 2) In the same section, the diagram of the agreement state model shows transitions from "PendingAndTerminating" to "Pending", and "ObservedAndTerminating" to "Observed". While I can understand the forward transitions (e.g. Pending to PendingAndTerminating), the reverse transions are puzzling, and not explicitly mentioned in the text. The text does say:"There may be domain dependent cases where an agreement completes normally while in PendingAndTerminating or ObservedAndTerminating states. These cases can be handled by allowing a domain-dependent sub-state of Terminated to indicate a normal completion prior to termination completion."But this doesn't quite explain the transitions in question. | Stephen Pickles |  | Ask Asit to add some explanatory text? (cf. Asit's comments below) (http://www.ogf.org/pipermail/graap-wg/2006-April/000390.html) As a matter of fact once the termination decision is reached by the provider, the agreement state will transition from either of these states to "Terminated" state immediately (while internal clean up may be taking place). This also means if the termination request is rejected, then the states revert back to their counterpart states. With this interpretation, a transition is possible from "PendingAndTerminating" to "ObservedAndTerminating" until the termination decision is reached. Furthermore, in "ObservedAndTerminatating" state, the service quality must be observed just as in "Observed" state. If we agree with this interpretation, I can add new transitions from "PendingAndTerminating" and "ObservedAndTerminating" to their counterparts. We also need new text to clarify the transitions from these states to "Terminated" -- triggered by when termination decision is made, (and not when internal clean up may be taking place).
19 | Comments on WS-Agreement | Section 8.2 Forms of Acceptance. The second last sentence: "The initiator MAY still determine the result of by other means such as querying the status of the resulting Agreement." appears to be missing some words between "of" and "by". | Stephen Pickles |  | … Will be fixed.:-(
| WS-Agreement with WS-Notification | WS-Notification is missing in the current specification: 1. notification of agreement acceptance is currently via custom port type. 2. the agreement status port does not extend the WS-Notification port type. However, WS-Agreement has a strong dependency of WS-ResourceProperty and almost all environment that support WS-RP also support WS-N, like Apache MUSE and GT4. So, I see little practical reason of excluding WS-N from the basis of WS- Agreement. | Tianchao Li
| Preference Example in Appendix 3 is Confusing | The preference example in appendix 3 defines several ServiceDescriptionTerms like job:numberOfCPUs, job:realMemorySize, which are confusing. I doubt if they are better defined as wsag:ServiceProperties instead of ServiceDescriptionTerms. In Section 4.2.5, job:networkBandwidth and job:numberOfCPUs are used as examples of ServiceProperties, and In Appendix 2 , the ServiceDescriptionTerms are used to define the Job with jsdl:JobDefinition. According to the definitions of ServiceDescriptionTerms and ServiceProperties, their distinctions seem to me not very clear: ServiceDescriptionTerms define the functionality that will be delivered under an agreement. Service Properties are used to define measurable and exposed properties associated with a service such as response time and throughput. | Tianchao Li |  | Number of CPUs as a resource *CAN BE* an SDT I think.
| Preference Example in Appendix 3 is Confusing | On the other hand, an extensive example of Service Properties and its relationship with SLOs is missing in the current specification. | Tianchao Li