## Discussion
Updated Date
Document Tracker |  | https://forge.gridforum.org/docman2/ViewCategory.php?group_id=71&category_id=659
Comment Tracker |  | https://forge.gridforum.org/forum/forum.php?forum_id=577
Draft |  | https://forge.gridforum.org/projects/graap-wg/document/WS-AgreementSpecificationDraft.doc/en
Comment-ID | Link | Contents | Posted By | Status | Resolution/Discussion | Reflected in Draft? | Page/Section/line | Owner | Done?
1 | Detailed comments from Stephen Pickles (grammatical) | 4. Page 5, section 1.1.1, first bullet, last sentence. “Service objective description will reference the elements defined in service description.” Even after two readings of the entire document, I still don’t understand what this means. Suggest revising the sentence. | Stephen Pickles
2 | Detailed comments from Stephen Pickles (grammatical) | 5. Page 6, section 1.1.1, last bullet. The meaning of “...whether or not this is created using message exchange defined via protocol or template as a starting point” escapes this reviewer. | Stephen Pickles
3 | Detailed comments from Stephen Pickles (grammatical) | 6. Page 6, para commencing “Relationship to other WS-* specificiations:” 3) Given the laudable intention of last bullet on this page, it is unfortunate that you have to refer to the “WS-Agreement protocol, ie. ...” instead of something more simpler and more concrete (e.g. “WS-Agreement Protocol”). The need for this could perhaps be obviated by carefully identifying and naming the parts of the specification which are intended for “independent use”. | Stephen Pickles
4 | Detailed comments from Stephen Pickles (grammatical) | 9. Page 7, section 1.2, last paragraph. It is unfortunate that square brackets are used in the same paragraph for two different purposes (references, and abstract property names). | Stephen Pickles |  | Suggestions for an easy way to get around appreciated.
5 | Detailed comments from Stephen Pickles (grammatical) | 11. Page 10, second paragraph (Template). This is the first mention of agreement factory. This is quite disruptive to the reader, who now has to figure out whether “agreement factory” means the same as “(agreement) responder”, and the clues are a long time coming. I think the issue arises because much of the specification (e.g. agreement structure and protocol) can be understood in terms of initiator and responder. The role of the responder as agreement factory seems to me to be crucial only when describing the binding to WSRF. You’re so close to being able to describe almost all initiator-responder interactions (including protocol and state model) abstractly, that it’s a real shame that the agreement factory concept leaks into the definition of template, which makes it harder to identify separable parts of the specification (in case you ever wanted to factorize the WS-Agreement specification into composable parts). I would suggest using “agreement responder” here, and elsewhere in the definitions introduce “agreement factory”, as a role that the responder takes on when the protocol is rendered in WSRF. | Stephen Pickles
6 | Detailed comments from Stephen Pickles (grammatical) | 12. Page 10, section 1.3, Namespace. 1) Is there not a more recent version of the wsa namespace? (Certainly there is a more recent version of WS-Addressing than March 2004.) Worth checking, if you haven’t already. 2) I don’t know whether this matters, but “wsrp” could also stand for “Web Services for Remote Portlets”. Is there any danger of a clash here? | Stephen Pickles |  | There will always be newer ones how to deal with this? (At lease there does exist 2004/August version and even more newer ones.)
7 | Detailed comments from Stephen Pickles (grammatical) | 16. Page 11, section 2.1, second paragraph, last sentence, use of “agreement resource”. This is the first real hint that an agreement is represented as a WS-Resource and comes as something of a surprise to the reader. If you accept my suggestion in my specific comment #11, you could introduce this notion earlier, perhaps at the same time as discussing “agreement factory” and WSRF. | Stephen Pickles
8 | Detailed comments from Stephen Pickles (grammatical) | 21. Page 13, section 3, layered model, figure 1. I see absolutely no need whatsoever to show so much detail in the service layer. In particular, the create() operation, existence of factory, and application instance seem to imply that the service layer is meant to be based on WSRF. While this may be so in many cases, it is certainly not a requirement of the WS-Agreement specification. This detail is over-specialised and out of scope. I strongly urge you to remove it. | Stephen Pickles
9 | Detailed comments from Stephen Pickles (grammatical) | 22. Page 14, section 3, paragraph numbered 2. Similar comments to the above apply. If you really want to discuss the creation of service or application instances in the service layer, then do so, but please do this only after you’ve discussed service consumption. Consumption’s always there. Creation isn’t. | Stephen Pickles
10 | Detailed comments from Stephen Pickles (grammatical) | 24. Page 17, first paragraph, ( /wsag:Context/wsag:AgreementInitiator ) Does the language permit this to be a WS-Name? If it is intended to allow WS-Names, it might be helpful to include this in the “MAY”s. | Stephen Pickles
11 | Detailed comments from Stephen Pickles (grammatical) | 25. Page 17, /wsag:Context/wsag :ExpirationTime Shouldn’t “service” read “resource” in “...to specify an Agreement service lifetime”? | Stephen Pickles
12 | Detailed comments from Stephen Pickles (grammatical) | 31. Page 20, section 4.2.3.1 I found myself struggling to understand whether “service description terms”, “ServiceDescriptionTerms”, and “Service Description Terms” (the abbreviation SDT has already been introduced for the last but is rarely used) are the same or subtly different things. Can you do something to spare your readers this confusion? Same question for /wsag:ServiceReference/@wsag:ServiceName (page 21, section 4.2.4) and /wsag:ServiceProperties/@wsag:ServiceName (page 22, section 4.2.5). | Stephen Pickles
13 | Detailed comments from Stephen Pickles (grammatical) | 35. Page 27, /wsag:BusinessValueList/wsag:Penalty (first paragraph on page) 36. Page 27, /wsag:BusinessValueList/wsag:Reward I do not understand the meaning of “they are applied alternatively, depending on the longest assessment interval applicable”. | Stephen Pickles
14 | Detailed comments from Stephen Pickles (grammatical) | 43. Page 30, /wsag:template/wsag:CreationConstraints Why “MAY”? If present, would they do anything other than provide constraints? | Stephen Pickles
15 | Detailed comments from Stephen Pickles (grammatical) | 47. Page 36, first paragraph, first sentence. “Based on the service term state, agreement states can be determined.” Do you really mean “agreement states” here? Section 7.1 has already established that the only agreement states are Pending, Observed, Rejected, Completed. | Stephen Pickles
16 | Detailed comments from Stephen Pickles (grammatical) | 50. Page 38, 8.2, second paragraph. “but the new Agreement MAY be in any state”. Really? | Stephen Pickles
17 | Detailed comments from Stephen Pickles (grammatical) | 52. Page 39, last sentence. “destroy no longer used resources”. No longer used by which party? | Stephen Pickles
18 | Detailed comments from Stephen Pickles (grammatical) | 54. Page 41, 9.1.1.2, /wsag:createAgreementResponse/createAgreementEPR Any reason why the returned EPR shouldn’t be a WS-Name? | Stephen Pickles
19 | Detailed comments from Stephen Pickles (grammatical) | 58. Page 49, 13 References. Are the IBM Developer Works URLs the definitive references for WS-Addressing, WS-Resource, etc? | Stephen Pickles
20 | Problems with Penalties and Rewards | 1) It would be extremely valuable if it was possible to describe a period of applicability of a Penalty (or Reward) element. This would make it easier to express a penalty/reward structure where some times are more important than others. 2) It would be valuable if it was possible to express more than one Unit/Expression pair per Penalty/Reward. This would enable things like compound compensation: "If you don't get your QoS, we'll give you $20 and a free run of BLAST!" | Donal Fellows
21 | Viewing an Agreement as a Contract | I believe that an Agreement must, in order to be useful across organizational boundaries, be regardable as a Contract. In order to meet this requirement, a few requirements must be added overall: 1) Both parties to the contract must (digitally) sign it. 2) Both parties must end up with their own copy of the contract. With this, either party that gets dissatisfied with the contract can go to an independent third party (such as a civil court) and argue their case for compensation. To meet the first requirement based on WS-Agreement requires that the Agreement Initiator digitally sign the AgreementOffer, and to meet the second requirement the Agreement Provider must respond with the offer digitally signed additionally by the provider (assuming she agrees to it, of course). Presumably the provider would also retain a copy in secure storage (much as companies keep paper copies of contracts in fireproof safes) but that is outside the scope of wsag. Note that having the agreement live in a service is *not* sufficient to meet this requirement, since it is not possible to strictly prohibit the provider from tampering with the document, and nor is it possible to prevent either side from destroying the agreement resource (something which it would be highly advantageous to do if the other side was taking the matter to court!) Of course, such contract-related things do not inherently say anything about the monitoring of the agreement, and they also significantly increase the computational cost of actually reaching the agreement. On the other hand, it means that all parties remain able to clear up any disputes they have over the agreement (ultimately a good thing for the overall grid, even if one of the parties would not agree in the short term). | Donal Fellows

## Grammatical
Updated Date
Document Tracker |  | https://forge.gridforum.org/docman2/ViewCategory.php?group_id=71&category_id=659
Comment Tracker |  | https://forge.gridforum.org/forum/forum.php?forum_id=577
Draft |  | https://forge.gridforum.org/projects/graap-wg/document/WS-AgreementSpecificationDraft.doc/en
Comment-ID | Link | Contents | Posted By | Status | Resolution/Discussion | Reflected in Draft? | Page/Section/line | Owner | Done?
1 | Detailed comments from Stephen Pickles (grammatical) | 1. Page 5, paragraph 2, last sentence. Suggest replacing “discipline-specific” by “domain-specific” to be consistent with language adopted later. | Stephen Pickles | tentatively done
2 | Detailed comments from Stephen Pickles (grammatical) | 2. Page 5, paragraph 5, 3rd last sentence. Should start “Section 9 introduces the port types” instead of “Section introduces the port types”. | Stephen Pickles | tentatively done | Why had it been originally dropped?
3 | Detailed comments from Stephen Pickles (grammatical) | 3. Page 5, section 1.1.1, first bullet. Suggest capitalizing “web service description language”. | Stephen Pickles | tentatively done
4 | Detailed comments from Stephen Pickles (grammatical) | 6. Page 6, para commencing “Relationship to other WS-* specificiations:” 1) Insert “The” between “specifications:” and “WS-Agreement”. 2) Delete spurious comma from “WS-ResourceProperties, , WS-ResourceLifetime”. | Stephen Pickles | tentatively done
5 | Detailed comments from Stephen Pickles (grammatical) | 7. Pages 6-7, table of external specifications. Check that specifications are properly named and latest versions referenced. | Stephen Pickles
6 | Detailed comments from Stephen Pickles (grammatical) | 8. Page 7, reference to OGSA profile. Do you mean to refer to this specific version? Should not the title of the OGSA profile be capitalized? | Stephen Pickles
7 | Detailed comments from Stephen Pickles (grammatical) | 10 Page 10, first paragraph. Suggest capitalizing all initials of “Service level objective”. | Stephen Pickles | tentatively done
8 | Detailed comments from Stephen Pickles (grammatical) | 13. Page 10, section 2. This is a really trivial comment, but I would write “wide range” or “broad scope”, but not “wide scope”. Probably just shows how much the English language is littered with cliché’s | Stephen Pickles | tentatively done
9 | Detailed comments from Stephen Pickles (grammatical) | 14. Page 11, section 2.1, first paragraph. Suggest replacing “submission of a job in a high performance or batch processing system” by simply “submission of a job to a batch processing system”. | Stephen Pickles | tentatively done
10 | Detailed comments from Stephen Pickles (grammatical) | 15. Page 11, section 2.1, second paragraph. Suggest replacing “an appropriate job description language for the service definition terms” by “service definition terms expressed in an appropriate job description language”. | Stephen Pickles | tentatively done
11 | Detailed comments from Stephen Pickles (grammatical) | 17. Page 11, section 2.2, second paragraph, first sentence. “agreement may be used” should read “agreements may be used”. | Stephen Pickles | tentatively done
12 | Detailed comments from Stephen Pickles (grammatical) | 18. Page 11, section 2.2, second paragraph, second last sentence. This is a little clumsy. Consider “... amounts, for example, a node with twice the memory size as a basic node could be valued three times more highly” | Stephen Pickles | tentatively done
13 | Detailed comments from Stephen Pickles (grammatical) | 19. Page 11, section 2.2, last paragraph, first sentence. Replace “additional dependency on software environment” by “additional dependencies on the software environment”. | Stephen Pickles | tentatively done
14 | Detailed comments from Stephen Pickles (grammatical) | 20. Page 12, section 2.3, second paragraph, last sentence. 1) Replace “as well as offers” by “also offers”. 2) Replace “investment fee structure” by “investment fee structures”. | Stephen Pickles | tentatively done
15 | Detailed comments from Stephen Pickles (grammatical) | 23. Page 16, /wsag:Agreement/wsag:Name 1) Suggest replacing “independent from” by “independent of”. 2) Suggest replacing “...beyond the Endpoint Reference...” by “...in addition to the Endpoint Reference...”. | Stephen Pickles | tentatively done
16 | Detailed comments from Stephen Pickles (grammatical) | 26. Page 17, /wsag:Context/wsag:TemplateID, last line Delete spurious “is” in “Context is MUST be set”. | Stephen Pickles | tentatively done
17 | Detailed comments from Stephen Pickles (grammatical) | 27. Page 19, /wsag:Terms/wsag:ServiceDescriptionTerm Suggest replacing “functional full or partial description” by “full or partial functional description” | Stephen Pickles | tentatively done
18 | Detailed comments from Stephen Pickles (grammatical) | 28. Page 19, /wsag:Terms/wsag:ServiceDescriptionTerm, last line. I dislike the wording “i.e. the information necessary to ‘instantiate’ the service”. The service layer does not have to be implemented in WSRF or OGSI (the language actually suggests OGSI). Consider instead “i.e. the information necessary to provide the service to the consumer.” | Stephen Pickles | tentatively done
19 | Detailed comments from Stephen Pickles (grammatical) | 29. Page 19, /wsag:Terms/wsag:ServiceProperties. The word “business” is unnecessary here. Delete it. | Stephen Pickles | tentatively done
20 | Detailed comments from Stephen Pickles (grammatical) | 30. Page 19, 4.2.3, Service Definition Terms, second line. The marks surrounding “existing of not” should be em-dashes, not hyphens. http://www.getitwriteonline.com/archive/091502.htm | Stephen Pickles | tentatively done
21 | Detailed comments from Stephen Pickles (grammatical) | 32. Page 22, section 4.2.5.1, /wsag:Variable/wsag:Location. Replace hyphen by em-dash. | Stephen Pickles | tentatively done
22 | Detailed comments from Stephen Pickles (grammatical) | 33. Page 25, /wsag:GuaranteeTerm/wsag:QualifyingCondition The wording “This element MAY appear to express a precondition...” is unfortunate. Suggest instead either “This element MAY appear in order to express a precondition...” or “This element when present expresses a precondition...” | Stephen Pickles | tentatively done
23 | Detailed comments from Stephen Pickles (grammatical) | 34. Page 26, Section 4.2.6.3, Business Value List, second paragraph, last sentence. I suggest replacing “makes appropriate resource allocation to maximize” by “allocates resources in order to maximize” | Stephen Pickles | tentatively done
24 | Detailed comments from Stephen Pickles (grammatical) | 37. Page 27, Section 4.2.6.3.1 Importance, first paragraph, second line Remove spurious “;”. | Stephen Pickles | Couldn't find
25 | Detailed comments from Stephen Pickles (grammatical) | 38. Page 27, Section 4.2.6.3.1 Importance, 2nd paragraph. The first sentence appears to be a rationale. Replacing “can” by “could” would make this clearer. | Stephen Pickles | tentatively done
26 | Detailed comments from Stephen Pickles (grammatical) | 39. Page 28, /wsag:Penalty/wsag:AssessmentInterval/wsag:Count “number of invocation” should read “number of invocations”. This is important, because you’re referring to the number of invocations (i.e. how many), not to a particular (numbered) invocation. | Stephen Pickles | tentatively done
27 | Detailed comments from Stephen Pickles (grammatical) | 40. Page 28, Section 4.2.6.3.3, Preference, first paragraph. I suggest replacing “makes appropriate resource allocation to maximize” by “allocates resources in order to maximize”. (See also comment 34). | Stephen Pickles | tentatively done
28 | Detailed comments from Stephen Pickles (grammatical) | 41. Page 28, 4.2.6.3.3 Preference, /wsag:Preference/wsag:ServiceTermReference Suggest instead “This element can appear multiple times. Each ServiceTermReference refers to a service term and represents an alternative way of achieving the associated service level objective. The corresponding utility (specified below) specifies the utility gained by achieving this objective.” (I’ve assumed that “ServiceTerm” really means the “service term” introduced in 4.2.1.) | Stephen Pickles | tentatively done
29 | Detailed comments from Stephen Pickles (grammatical) | 42. Page 30, /wsag:template, last sentence Replace “and” by “an” in “contains and agreement”. | Stephen Pickles | tentatively done
30 | Detailed comments from Stephen Pickles (grammatical) | 44. Page 33, 5.1.2 Free-form Constraints, first para. Suggest replacing the sentence “This specification does not define a constraint language but proposes to choose a suitable existing one” by “This specification does not define a constraint language but allows a suitable existing one to be chosen.” | Stephen Pickles | tentatively done
31 | Detailed comments from Stephen Pickles (grammatical) | 45. Page 35, 7.2, bullet “Ready” Replace “start now” by “now start”. | Stephen Pickles | tentatively done
32 | Detailed comments from Stephen Pickles (grammatical) | 46. Page 35, 7.2, bullet “Completed”. Suggest replacing first sentence by “This service cannot be used any more and any service provider activity, e.g. performing a job, is finished.” | Stephen Pickles | tentatively done
33 | Detailed comments from Stephen Pickles (grammatical) | 48. Page 37, sentence following diagram. Replace “is” by “are” in “semantics of the states is as follows:” | Stephen Pickles | tentatively done
34 | Detailed comments from Stephen Pickles (grammatical) | 49. Page 37, /wsag:GuaranteeTermState “This element has the contains one element of the following:” Fix this! | Stephen Pickles | tentatively done
35 | Detailed comments from Stephen Pickles (grammatical) | 51. Page 39, 9, bullet 5. Period needed after “symmetric”. | Stephen Pickles | tentatively done
36 | Detailed comments from Stephen Pickles (grammatical) | 53. Page 40, second paragraph. “Full WSDL ... Appendix.” Which Appendix? | Stephen Pickles | tentatively done
37 | Detailed comments from Stephen Pickles (grammatical) | 55. Page 45, 9.4.4, Note, last sentence. Replace “fine-grain” by “fine-grained”. | Stephen Pickles | tentatively done
38 | Detailed comments from Stephen Pickles (grammatical) | 56. Page 48, 10, Process, bullet 1. Insert “of” after “one” in “constraints of one the templates”. | Stephen Pickles | tentatively done
39 | Detailed comments from Stephen Pickles (grammatical) | 57. Page 49, 12 Acknowledgements Replace “Steven Pickles” by “Stephen Pickles”. Insert comma before “ Volker Sander”. | Stephen Pickles | tentatively done